{"text_format":"1","workbook":"xlsx","n_sheets":1,"sheets":["３目論見書"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":0,"defined_names":4,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"３目論見書","index":0,"n_rows":42,"n_cols":19,"rows_kept":42,"cut":false,"hidden":false,"merged":[[6,2,7,2],[6,12,14,12],[6,13,14,13],[6,17,7,17],[9,2,11,2],[9,5,11,5],[11,17,14,17],[2,0,2,18],[4,3,4,5],[4,6,4,7],[4,8,4,9],[4,12,4,13],[15,2,16,2],[15,12,23,12],[15,13,23,13],[15,17,16,17],[18,2,20,2],[18,5,20,5],[20,17,23,17],[24,2,25,2],[24,12,32,12],[24,13,32,13],[24,17,25,17],[27,2,29,2],[27,5,29,5],[29,17,32,17],[33,2,34,2],[33,12,41,12],[33,13,41,13],[33,17,34,17],[36,2,38,2],[36,5,38,5],[38,17,41,17]]}
[]
["様式第二（第五条関係）"]
["目　　　　論　　　　見　　　　書"]
["査定：第○次",null,"査定区分：本省　査定",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"長　野　県"]
[null,null,null,"位　　　　置",null,null,"申　請　額(千円)",null,"決　定　額(千円)",null,null,null,"設　　計　　概　　要"]
["工事\n番号","事務所名\n市町村名","河 川 名\n路 線 名","郡　市","町　村","大　字","工事費","内転属又\nは内未成　　","工事費","内転属又\nは内未成","査定\n方法","緊急\n順位","申　　請","決　　定","　　　　経 済 効 果",null,null,"異常気象","摘　　要"]
[null,null,"市町村道(その他)",null,null,null,null,null,null,null,null,null,"復旧長 L=15.7m\n幅員 W=2.6-4.0m\nブロック積 A=64m2\n植生基材吹付 A=390m2\n水路撤去設置 L=10m\n水路設置 L=31m","復旧長 L=15.7m\n幅員 W=2.6-4.0m\nブロック積 A=64m2\n植生基材吹付 A=390m2\n水路撤去設置 L=10m\n水路設置 L=31m","住家及びこれに準ずる建物",5,"戸",16095,"積算方法"]
[null,null,null,null,null,null,"工事費総額","工事費総額","工事費総額","工事費総額",null,null,null,null,"交通量自動車",20,"台",null,"積上"]
[null,null,null,null,null,null,9853,0,9819,0,null,null,null,null,"田、畑及び山林",5,"ha","2016-04-07","関連又は助成事業"]
[null,null,"村道3033号線",null,null,"菅","内応急仮工事","内応急仮工事","内応急仮工事","内応急仮工事",null,null,null,null,0,0,0,"～",0]
[2,"白馬村",null,"　","白馬村",null,132,0,128,0,"実査","C",null,null,0,0,0,"2016-04-08","応急仮工事適用条項"]
[null,"　",null,null,null,null,"内工事雑費","内工事雑費","内工事雑費","内工事雑費",null,null,null,null,null,null,null,"豪雨","９．(一)．ロ"]
[null,null,null,null,null,null,144,0,144,0,null,null,null,null,null,null,null,null,"内未成・内転属"]
[null,null,null,null,null,null,"国庫負担対象額","国庫負担対象額","国庫負担対象額","国庫負担対象額",null,null,null,null,null,null,null,null,"前災害発生年・番号"]
[null,null,null,null,null,null,9709,0,9675,0,null,null,null,null,null,null,null,null,0]
[null,null,"主要地方道",null,null,null,null,null,null,null,null,null,"復旧延長　　L=38.0m\n垂直擁壁工   L=10.0m H=3.0～3.5m A=34.5m2\n車道舗装工   A=18m2\n小型擁壁工   L=10.0m H=0.15～100m V=4m3\n防護柵工　　　L=38m\n崩土除去　　　V=12m3","復旧延長　　L=36.0m\n垂直擁壁工   L=10.0m H=3.0～3.5m A=34.5m2\n車道舗装工   A=18m2\n小型擁壁工   L=10.0m H=0.15～100m V=4m3\n防護柵工　　　L=36m\n崩土除去　　　V=12m3","交通量自動車",3209,"台/日",16095,"積算方法"]
[null,null,null,null,null,null,"工事費総額","工事費総額","工事費総額","工事費総額",null,null,null,null,0,0,0,null,"積上"]
[null,null,null,null,null,null,7054,0,6989,0,null,null,null,null,0,0,0,"2016-04-07","関連又は助成事業"]
[null,null,"乗鞍岳線",null,null,"三本滝上","内応急仮工事","内応急仮工事","内応急仮工事","内応急仮工事",null,null,null,null,0,0,0,"～",0]
[5,"松本",null,"松本市","　",null,0,0,0,0,"実査","B",null,null,0,0,0,"2016-04-08","応急仮工事適用条項"]
[null,"建設事務所",null,null,null,null,"内工事雑費","内工事雑費","内工事雑費","内工事雑費",null,null,null,null,null,null,null,"豪雨",0]
[null,null,null,null,null,null,104,0,103,0,null,null,null,null,null,null,null,null,"内未成・内転属"]
[null,null,null,null,null,null,"国庫負担対象額","国庫負担対象額","国庫負担対象額","国庫負担対象額",null,null,null,null,null,null,null,null,"前災害発生年・番号"]
[null,null,null,null,null,null,6950,0,6886,0,null,null,null,null,null,null,null,null,0]
[null,null,"一般国道",null,null,null,null,null,null,null,null,null,"復旧延長　L=35m\n法面工\n　モルタル吹付工　A=530m2\n　吹付枠工\n　　梁断面300型　L=820m\n　　梁断面500型　L=33m","復旧延長　L=35m\n法面工\n　モルタル吹付工　A=530m2\n　吹付枠工\n　　梁断面300型　L=820m\n　　梁断面500型　L=33m","鉄道及び道路",4111,"台/日",16095,"積算方法"]
[null,null,null,null,null,null,"工事費総額","工事費総額","工事費総額","工事費総額",null,null,null,null,0,0,0,null,"積上"]
[null,null,null,null,null,null,64489,0,64489,0,null,null,null,null,0,0,0,"2016-04-07","関連又は助成事業"]
[null,null,"361号",null,null,"明澤橋","内応急仮工事","内応急仮工事","内応急仮工事","内応急仮工事",null,null,null,null,0,0,0,"～",0]
[6,"伊那",null,"伊那市","　",null,0,0,0,0,"実査","B",null,null,0,0,0,"2016-04-08","応急仮工事適用条項"]
[null,"建設事務所",null,null,null,null,"内工事雑費","内工事雑費","内工事雑費","内工事雑費",null,null,null,null,null,null,null,"豪雨",0]
[null,null,null,null,null,null,954,0,954,0,null,null,null,null,null,null,null,null,"内未成・内転属"]
[null,null,null,null,null,null,"国庫負担対象額","国庫負担対象額","国庫負担対象額","国庫負担対象額",null,null,null,null,null,null,null,null,"前災害発生年・番号"]
[null,null,null,null,null,null,63535,0,63535,0,null,null,null,null,null,null,null,null,0]
[]
[null,null,null,null,null,null,"工事費総額","工事費総額","工事費総額","工事費総額"]
[null,null,null,null,null,null,81396,0,81297,0]
[null,null,null,null,null,3,"内応急仮工事","内応急仮工事","内応急仮工事","内応急仮工事"]
["計",null,null,null,null,null,132,0,128,0]
[null,null,null,null,null,null,"内工事雑費","内工事雑費","内工事雑費","内工事雑費"]
[null,null,null,null,null,null,1202,0,1201,0]
[null,null,null,null,null,null,"国庫負担対象額","国庫負担対象額","国庫負担対象額","国庫負担対象額"]
[null,null,null,null,null,null,80194,0,80096,0]